## Worksheet
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 Delivered | LT Delivered | V2 Reopen | LT Reopen | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | 2021: LCW 10/7 -10/21 | 55 | 28 | 14 | 41 | 5 | 0 | 10 | 17 | 9 | 36% | 0% | 71% | 41% | 51% | Row Labels | Sum of V2 Delivered | Sum of LT Delivered
PROJECT HEALTH DASHBOARD | [7 empty] | 2021: LCW 9/23 - 10/7 | 57 | 15 | 15 | 42 | 5 | 0 | 10 | 32 | 10 | 33% | 0% | 67% | 76% | 26% | 2021: LCW 10/7 -10/21 | 14 | 41
[8 empty] | 2021: LCW 10/7 -10/21 | 57 | 15 | 15 | 42 | 5 | 0 | 10 | 32 | 10 | 33% | 0% | 67% | 76% | 26% | 2021: LCW 9/23 - 10/7 | 15 | 42
[8 empty] | 2021: LCW 9/23 - 10/7 | 52 | 44 | 19 | 33 | 5 | 0 | 3 | 5 | 14 | 26% | 0% | 16% | 15% | 85% | 2021: LCW 10/7 -10/21 | 15 | 42
[8 empty] | 2021: LCW 9/9 - 9/23 | 58 | 50 | 40 | 18 | 3 | 0 | 3 | 5 | 37 | 8% | 0% | 8% | 28% | 86% | 2021: LCW 9/23 - 10/7 | 19 | 33
| Project Name | Consumer Web |  |  |  | Status Date | 04-Oct-2021 | 2021: LCW 8/26 - 9/9 | 48 | 45 | 19 | 29 | 0 | 3 | 3 | 0 | 19 | 0% | 10% | 16% | 0% | 94% | 2021: LCW 9/9 - 9/23 | 40 | 18
| Delivery Manager | Mamatha Joshi | [5 empty] | 2021: LCW 8/12 - 8/26 | 55 | 28 | 14 | 41 | 5 | 0 | 10 | 17 | 9 | 36% | 0% | 71% | 41% | 51% | 2021: LCW 8/26 - 9/9 | 19 | 29
| Project Manager/Lead | Sakshee |  |  |  | Overall Status | Amber | LCW 9/23 - 10/7 | 56 | 48 | 44 | 12 | 0 | 3 | 3 | 5 | 44 | 0% | 25% | 7% | 42% | 86% | 2021: LCW 8/12 - 8/26 | 14 | 41
| Client Poc | - | [5 empty] | LCW 10/8 - 11/7 | 56 | 48 | 44 | 12 | 3 | 0 | 3 | 5 | 41 | 7% | 0% | 7% | 42% | 86% | LCW 9/23 - 10/7 | 44 | 12
| Client Feedback | - | [20 empty] | LCW 10/8 - 11/7 | 44 | 12
| Team Allocation | 0 | [20 empty] | Grand Total | 224 | 270
| Offshore Team | Allocated | 6 | Billable | 6 | [17 empty] | 2021: LCW 10/7 -10/21 | 14 | 41
| Onsite Team | Allocated | 0 | [19 empty] | 2021: LCW 9/23 - 10/7 | 15 | 42
[23 empty] | 2021: LCW 10/7 -10/21 | 15 | 42
[23 empty] | 2021: LCW 9/23 - 10/7 | 19 | 33
[23 empty] | 2021: LCW 9/9 - 9/23 | 40 | 18
[23 empty] | 2021: LCW 8/26 - 9/9 | 19 | 29
[23 empty] | 2021: LCW 8/12 - 8/26 | 14 | 41
[23 empty] | LCW 9/23 - 10/7 | 44 | 12
[23 empty] | LCW 10/8 - 11/7 | 44 | 12