## Worksheet
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 Delivered | LT Delivered | V2 Reopen | LT Reopen | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | 2021: LCW 7/29 - 8/12 | 48 | 34 | 25 | 23 | 0 | 3 | 5 | 9 | 25 | 0% | 13% | 20% | 39% | 71% | Row Labels | Sum of V2 Delivered | Sum of LT Delivered
PROJECT HEALTH DASHBOARD | [7 empty] | On Deck- 2021: LCW 8/12 - 8/26 | 39 | 8 | 30 | 9 | 3 | 0 | 25 | 6 | 27 | 10% | 0% | 83% | 67% | 21% | 2021: LCW 7/29 - 8/12 | 25 | 23
[8 empty] | On Deck- 2021: LCW 8/26 - 9/9 | 56 | 19 | 35 | 21 | 0 | 5 | 29 | 8 | 35 | 0% | 24% | 83% | 38% | 34% | On Deck- 2021: LCW 8/12 - 8/26 | 30 | 9
[8 empty] | On Deck- 2021: LCW 9/9 - 9/23 | 48 | 19 | 39 | 9 | 12 | 0 | 26 | 3 | 27 | 31% | 0% | 67% | 33% | 40% | On Deck- 2021: LCW 8/26 - 9/9 | 35 | 21
[8 empty] | 2021: LCW 9/23 - 10/7 | 39 | 8 | 30 | 9 | 3 | 0 | 25 | 6 | 27 | 10% | 0% | 83% | 67% | 21% | On Deck- 2021: LCW 9/9 - 9/23 | 39 | 9
| Project Name | Consumer Web |  |  |  | Status Date | 04-Oct-2021 | 2021: LCW 10/7 -10/21 | 57 | 15 | 31 | 26 | 9 | 6 | 21 | 21 | 22 | 29% | 23% | 68% | 81% | 26% | 2021: LCW 9/23 - 10/7 | 30 | 9
| Delivery Manager | Mamatha Joshi | [5 empty] | 2021: LCW 10/21 -11/4 | 48 | 34 | 25 | 23 | 0 | 3 | 5 | 9 | 25 | 0% | 13% | 20% | 39% | 71% | 2021: LCW 10/7 -10/21 | 31 | 26
| Project Manager/Lead | Sakshee |  |  |  | Overall Status | Amber | [15 empty] | 2021: LCW 10/21 -11/4 | 25 | 23
| Client Poc | - | [20 empty] | Grand Total | 215 | 120
| Client Feedback | -
| Team Allocation | 0
| Offshore Team | Allocated | 6 | Billable | 6
| Onsite Team | Allocated | 0
[23 empty] | Sprint | V2 Delivered | LT Delivered
[23 empty] | 2021: LCW 7/29 - 8/12 | 25 | 23
[23 empty] | On Deck- 2021: LCW 8/12 - 8/26 | 30 | 9
[23 empty] | On Deck- 2021: LCW 8/26 - 9/9 | 35 | 21
[23 empty] | On Deck- 2021: LCW 9/9 - 9/23 | 39 | 9
[23 empty] | 2021: LCW 9/23 - 10/7 | 30 | 9
[23 empty] | 2021: LCW 10/7 -10/21 | 31 | 26
[23 empty] | 2021: LCW 10/21 -11/4 | 25 | 23