## Worksheet
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 Delivered | LT Delivered | V2 Reopen | LT Reopen | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | 2021: SC 10.2 (10.19 - 11.2) | 38 | 32 | 15 | 23 | 2 | 3 | 0 | 6 | 13 | 13% | 13% | 0% | 26% | 84% | Row Labels | Sum of V2 Delivered | Sum of LT Delivered
PROJECT HEALTH DASHBOARD | [7 empty] | 2021: SC 10.1 (10.5 - 10.19) | 40 | 21 | 12 | 28 | 0 | 2 | 0 | 19 | 12 | 0% | 7% | 0% | 68% | 53% | 2021: SC 10.2 (10.19 - 11.2) | 15 | 23
[23 empty] | 2021: SC 10.1 (10.5 - 10.19) | 12 | 28
[23 empty] | Grand Total | 27 | 51
| Project Name | Snapcap |  |  |  | Status Date | 10-Nov-2021
| Delivery Manager | Mamatha Joshi
| Project Manager/Lead | Jayant Dharmadhikari |  |  |  | Overall Status | Green
Client Poc
Client Feedback
| Team Allocation | 0
| Offshore Team | Allocated | 2 | Billable | 2
| Onsite Team | Allocated | 3
[23 empty] | Sprint | V2 Delivered | LT Delivered
[23 empty] | 2021: SC 10.2 (10.19 - 11.2) | 15 | 23
[23 empty] | 2021: SC 10.1 (10.5 - 10.19) | 12 | 28