## Worksheet
[8 empty] | Week Starting On | Planned Story Points | Actual Delivered | V2 Delivered | LT Delivered | V2 Rework | LT Rework | V2 Carryover | LT Carryover | QA Passed | V2 Reopen Percentage | LT Reopen Percentage | V2 Carryover Percentage | LT Carryover Percentage | Planned Vs Completed ratio
[8 empty] | 2021: LCW 10/7 -10/21 | 55 | 28 | 14 | 41 | 5 | 0 | 10 | 17 | 9 | 36% | 0% | 71% | 41% | 51% | Row Labels | Sum of V2 Delivered | Sum of LT Delivered
PROJECT HEALTH DASHBOARD | [7 empty] | 2021: LCW 9/23 - 10/7 | 57 | 15 | 15 | 42 | 15 | 42 | 10 | 32 | 0 | 100% | 100% | 67% | 76% | 26% | 2021: LCW 10/7 -10/21 | 14 | 41
[23 empty] | 2021: LCW 9/23 - 10/7 | 15 | 42
[23 empty] | Grand Total | 29 | 83
| Project Name | Consumer Web |  |  |  | Status Date | 20-Oct-2021
| Delivery Manager | Raj Makhija
| Project Manager | Sakshee and Brinto |  |  |  | Overall Status | Amber
| Client Poc | -
| Client Feedback | -
| Team Allocation | 0 | [20 empty] | Sprint | V2 Delivered | LT Delivered
| Offshore Team | Allocated | 6 | Billable | 6 | [17 empty] | 2021: LCW 10/7 -10/21 | 14 | 41
| Onsite Team | Allocated | 0 | [19 empty] | 2021: LCW 9/23 - 10/7 | 15 | 42